## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09
|  |  |  | 117 | 108 | 99 | 90 | 81 | 72 | 63 | 54 | 45 | 36 | 27 | 18 | 9 | 0 | Ideal Burndown
|  |  | 160 | 117 | 108 | 90 | 84 | 79 | 68 | 63 | 49 | 50 | 40 | 27 | 18 | 12 | 0 | Remaining Hrs (Total)
Enable all users to place book in shopping cart | Authentication API | Saylee | 40 | 0 | 4 | 1 | 1 | 3 | 2 | 4 | 0 | 2 | 3 | 2 | 3 | 1 | 0
| AWS Deployment + Documentation, Journals | Saylee | 20 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Add Cards API | Chaitrali | 40 | 0 | 4 | 2 | 1 | 2 | 1 | 4 | 0 | 2 | 4 | 2 | 2 | 2 | 0
| AWS Deployment + Documentation, Journals | Chaitrali | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Managed Order API | Prathyusha | 20 | 0 | 5 | 2 | 1 | 3 | 1 | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 0
| Front-End Code, Database | Prathyusha | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payments and Store API | Anand | 40 | 0 | 5 | 1 | 0 | 0 | 1 | 3 | 0 | 3 | 3 | 3 | 2 | 2 | 0
Upgrade Transaction Processing Module (Must be able to support 500 Transactions/Sec | Front-End Code, Project Setup, Burndown Chart | Anand | 10 | 2 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Demo Presentations | Anand + Saylee | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
| Demo Presentations | Chaitrali + Prathyusha | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Team:
Sanjay | 20 hours / Week
Jing | 20 hours / Week
Phillip | 20 hours / Week
Tracy | 20 hours / Week
Sarah
Sam
Total Available Hours During Sprint: | 160